Scope of Work

Team Members: William Brown
Date Submitted: February 2nd, 2026
Submitted to: Professor Wissam

Project Goals:
The goal of this project is to provide and in depth analysis of air quality across Nebraska using AirPurple monitor data. The Client has requested four main tasks: (1) The top five locations in Nebraska with the highest pollutant levels, (2) an analysis on what caused the most sever pollutant days, (3) an analysis of humidity and temperature’s affects on air quality, and (4) find days posed health risks based off the AQI scale and find potential causes.

Project Tasks:

High Pollutant Locations
Air pollutants data will be extracted from the AirPurple monitors, organized in an Excel spreadsheet and processed with DataFrames using Python. Specifically we will look at which locations in Nebraska have the highest levels of VOC, PM 2.5, and PM 10.0. The data with be cleaned into tables with the 5 highest mean and mode of each pollutant and the associated location. These tables and all Python code throughout the project will be provided to the client.

Pollutant Heavy Days
The team will take the DataFrames and sort them by the highest value each type of pollutant. Taking the maximum measurement from each pollutant, we will look at when and where they happened. Using those dates and locations we will look at outside factors that could have contributed to the low air quality. Specifically looking for things such as weather, industry emissions, or natural disasters. A report will be made with each date/ location with potential causes for increased pollutants.

Humidity and Temperature on Air Quality
The AirPurple readings will be organized by humidity and categorized into either low, high, or very high humidity. Then we will calculate the mean pollutant level for each category as well as plot the pollutant levels against the humidity to look for any relationship. The same thing will be done for temperature, diving it into below freezing, cool, warm, and hot. Our team will provide these graphs as well as an interpretation.

AQI Health Risks Across Nebraska
The EPA’s AQI rating system will be used to determine when air quality is hazardous and who’s primarily effected. PM 2.5 and PM 10.0 readings will be filtered to only include readings beyond the “Unhealthy” threshold. With these readings the dates and locations will be studied to look for potential outside factors. Similarly to the pollutant heavy days, a report will be constructed with all the dates and locations with potential causes for elevated PM 2.5 and PM 10.0 levels.

Deliverables:
Raw data files
Python scripts
GitHub link with project data (python code, CSV data, README)
SOW
ACD
Final Report